## Sheet
Project Name: | Sofia
Description: | Sofia is an AI assistant
Stakeholders: | Jai, Rohan, Ishan, Piyush
Target End Date: | 2025-01-22
Milestone Name | Start Date | End Date | Milestone Owner | Progress | Status
PD | 2024-02-01 | 2024-02-29 | Piyush | 100
CR Discussion | 2024-02-15 | 2024-02-29 | Tannu | 100
Integration Testing | 2024-03-01 | 2024-06-30 | Janhvi! | 96 | Accepted
E2E testing | 2024-03-07 | 2024-03-08 | Harshit | 86 | Accepted
Final Demo | 2024-03-08 | 2024-03-12 | Jai | 100
Final BU Sign Off | 2024-01-18 | 2024-02-23 |  | 100 | Accepted
Ops Readiness | 2024-03-14 | 2024-03-19 | Ishan | 100 | Accepted
UAT | 2024-03-20 | 2024-03-21 | Ritvik | 98 | Accepted
Go-NoGo Decision | 2024-03-22 | 2024-03-27 | Jai | 59 | Accepted
GO Live Activity | 2024-03-28 | 2024-03-29 | Jai | 100
GO Live | 2024-03-29 | 2024-04-26 | Jai | 89 | Accepted
Ramp Activity | 2024-03-29 | 2024-05-10 | Jai | 90 | Accepted
Post Production Support | 2024-04-03 | 2024-09-07 | Jai | 60
d - Dependency on Project 5 | 2024-06-14 | 2024-06-27 | Umesh | 58 | Accepted
Requirements | 2024-06-27 | 2024-06-27 | Jai | 98
d - Dependency on Project 1_new | 2024-07-01 | 2024-07-31 | N/A | 30
d - Dependency on Project 1 | 2024-05-02 | 2024-07-10 | N/A | 0